## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Gagan B T | 2026-01-09 | Windows terminal threw an encoding error on Unicode symbols. | Sprint 1 | Gagan B T | Bug | Changed terminal prints to plain ASCII text. | 2026-01-09 | Closed | Works on all Windows command prompts now.
2 | Gagan B T | 2026-02-09 | Text cleaner was leaving 3 blank lines instead of 2. | Sprint 1 | Gagan B T | Logic Error | Updated text cleaner code in preprocessor.py. | 2026-02-09 | Closed | Tested and verified with unit test.
3 | Gagan B T | 2026-02-09 | CSV files with semicolon (;) separators were not reading properly. | Sprint 1 | Gagan B T | Ingestion | Added automatic delimiter detection in csv_loader.py. | 2026-02-09 | Closed | Now reads comma, semicolon, and tab CSV files.
4 | Gagan B T | 2026-04-09 | Scope agent was not extracting all the scope and deliverable details from the uploaded document. | Sprint 2 | Gagan B T | Logic Error | Updated the scope agent prompt and checked the retrieved document context before extraction. | 2026-04-09 | Closed | Tested with SLTS requirements document and verified the extracted goals, scope, deliverables, and constraints.
5 | Gagan B T | 2026-06-09 | Risk agent was returning incomplete results when the required risk information was not clearly present in the document. | Sprint 2 | Gagan B T | AI Output | Updated the risk agent instructions to use only the retrieved document content and evidence. | 2026-06-09 | Closed | Tested with project documents and verified that unsupported risks are not added.
6 | Gagan B T | 2026-08-09 | Blocker agent was not handling missing owner and due date information properly. | Sprint 2 | Gagan B T | Data Validation | Updated the agent handling to keep owner and due date as null when they are not available. | 2026-08-09 | Closed | Tested with project documents containing incomplete action item details.
7 | Gagan B T | 28/9/2026 | Health score weights were initially implemented incorrectly as 1/1/1/1/1/0.75 instead of the published 20/20/20/15/15/10 formula. | Sprint 3 | Gagan B T | Logic Error | Corrected the Project Health Scoring formula to use Scope Clarity 20%, Timeline Risk 20%, Blocker Count 20%, Risk Exposure 15%, Deliverable Progress 15%, and Documentation Completeness 10%. Added a regression test to prevent the published weights from drifting. |  | Closed | Health score calculations were verified as deterministic against the real project data.
8 | Gagan B T | 30/9/2026 | GeneratedDocsPanel referenced a non-existent MarkdownView component. | Sprint 3 | Gagan B T | User Interface | Created a dependency-free renderer using React elements instead of the missing MarkdownView dependency. |  | Closed | Generated documentation can be rendered without dangerouslySetInnerHTML.
9 | Gagan B T | 2026-01-10 | Generated documentation needed to remain grounded in uploaded project documents and existing Milestone 2 analysis instead of creating unsupported project information. | Sprint 3 | Gagan B T | AI Output | Generation logic was implemented to use existing project documents and Milestone 2 outputs. Unsupported fields are represented as not specified rather than inferred. |  | Closed | Generated User Stories, Risk Register and Action Item List were validated against project source data.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others